## Testplan
ID | Feature | Stimulus | Checker | Coverage item | Priority | Status | Notes
RST001 | After reset: tx=1, busy=0, rdy=0, data_out=0, TX and RX FSMs in IDLE. Must hold for a reset applied after traffic, not only at time 0. | Hold rst >= 5 clks at sim start; re-apply rst after >= 1 completed frame. | a_rst_values | c_rst_after_traffic | P1 | Not started | Sync reset, so the property uses ¦=> (new values visible next cycle). No 'disable iff (rst)' on this property. tx is the internal tx_rx wire: bind into UART or expose the pin.
RST002 | Reset during a TX frame aborts it: tx returns to 1, busy to 0, and the next frame sent after reset is correct. | wr_en, then rst at a random point inside START, DATA or STOP; then send a fresh byte. | a_rst_values; mon_tx (frame cut by rst is flagged 'aborted', not decoded); scb_tx drops the aborted byte | c_rst_mid_tx; cp_tx_state_at_rst (bins START, DATA, STOP) | P1 | Not started | mon_tx must treat a frame cut by rst as aborted, not as a protocol error.
RST003 | Reset during an RX frame: no rdy for the interrupted byte; the next complete frame is received correctly. | drv_rx sends a frame; assert rst at a random point in START, DATA_OUT or STOP; idle the line for one frame time; send a good frame. | scb_rx: no rdy for the interrupted byte; next byte matches | cp_rx_state_at_rst (bins START, DATA_OUT, STOP) | P2 | Not started | Spec decision: after a mid-frame reset the line still carries the rest of the old frame, so a 0 data bit looks like a start bit and RX may emit one junk byte. Either idle the line for a full frame before checking, or let scb_rx tolerate one junk byte. Needs drv_rx.
RST004 | Reset released while the rx line is low: no valid byte is produced while the line stays low. | Hold rx low, assert then release rst, keep rx low for >= 3 frame times. | scb_rx: rdy never rises during the low period | c_rst_release_rx_low | P3 | Not started | Needs drv_rx. Same checker as RXE004 (break), different reset timing.
RST005 | No X/Z on tx, busy, rdy or data_out once reset has been applied. | Any test; checking starts at the first reset release. | a_no_x (ADD SVA: !$isunknown({tx,busy,rdy,data_out})) | c_no_x (vacuity) | P1 | Not started | Outputs may legitimately be X before the first reset, so do not check then.
BRG001 | tx_tick is a one-cycle pulse exactly every clk_freq/baud_rate clocks (5208 at 50 MHz / 9600). | Run >= 20 ticks after reset with default parameters; repeat per config in PAR001. | a_tx_tick_period | c_tx_tick_pair (tx_tick ##CLKS_PER_BIT tx_tick) - ADD | P1 | Not started | CLKS_PER_BIT must match the integer division in baud_rate_generator.sv.
BRG002 | rx_tick is a one-cycle pulse every clk_freq/(16*baud_rate) clocks (325 at default), about 16 rx_ticks per bit. | Run >= 100 rx_ticks after reset; repeat per config in PAR001. | a_rx_tick_period (ADD SVA) | c_rx_tick_pair - ADD | P1 | Not started | 16 x 325 = 5200 clocks vs TX 5208: 0.15% mismatch at default. See Param_Calc for other configs.
TXF001 | Frame format: idle high, 1 start bit (0), 8 data bits LSB first, 1 stop bit (1), no parity. | Directed bytes 0x00, 0xFF, 0x55, 0xAA, 0x01, 0x80, 0xA5 plus random bytes, one at a time with idle gaps. | mon_tx independently decodes the tx line; decoded byte == data_in (scb_tx) | cg_tx_data.cp_data (0x00, 0xFF, 0x55, 0xAA, 0x01, 0x80, walking-1, walking-0, other) | P1 | Not started | Do not use RX as the decoder: loopback hides bit-order bugs. 0x01 and 0x80 catch MSB/LSB order errors only with an independent monitor.
TXF002 | Every bit (start, 8 data, stop) lasts exactly CLKS_PER_BIT clocks; the start bit begins on a tx_tick. | Any frame; measure transitions in clocks. | mon_tx bit-width check == CLKS_PER_BIT; a_tx_changes_on_tick | c_tx_changed (vacuity) | P1 | Not started | Measure against a bit-time grid anchored on the start-bit falling edge. A stop bit followed by idle can only be checked as >= 1 bit period.
TXF003 | tx idles high whenever busy=0, including after reset and between frames. | Idle >= 2 frame times; after each frame; after reset. | a_tx_idle_high | c_tx_idle_high (vacuity) | P1 | Not started
TXF004 | Start bit begins on the next tx_tick after an accepted wr_en: latency 1 to CLKS_PER_BIT clocks (up to one bit period), including wr_en landing in the same cycle as a tx_tick. | Issue wr_en at randomised phases relative to tx_tick, including the tick cycle and the cycles either side. | a_start_latency (ADD SVA: (wr_en && !busy) ¦-> ##[1:CLKS_PER_BIT+1] !tx) | cp_wr_phase (tick-1, tick, tick+1, early, mid, late in the tick period) | P2 | Not started | IDLE ignores tx_tick, so wr_en in the tick cycle waits a full period - worth hitting on purpose. Bound has +1 slack; tighten after the first run.
TXI001 | wr_en while busy is dropped silently: the current frame is unaffected and no second frame is queued. | Pulse wr_en with a different data_in at random times in START, DATA and STOP. | scb_tx (only the first byte appears); mon_tx | c_wr_en_while_busy; cp_wr_en_state (START, DATA, STOP) | P1 | Not started | No busy-write error flag exists - document as accepted behaviour.
TXI002 | data_in is latched when wr_en is accepted; changing data_in afterwards does not alter the frame. | Drive data_in = X with wr_en, change it to ~X on the next cycle and keep changing it during the frame. | scb_tx / mon_tx: frame decodes to X | cp_data_in_change_after_wr (hit) | P1 | Not started
TXI003 | Back-to-back: wr_en on the first cycle busy is low starts the next frame after exactly one full stop-bit period; no data lost. | After each busy fall, re-issue wr_en immediately; >= 100 frames. | mon_tx (stop-to-start gap == CLKS_PER_BIT); scb_tx | c_wr_en_at_busy_fall (hit count >= 100) | P1 | Not started | busy falls when the stop bit begins. The stop bit is a full period only because START waits for the next tick; this test confirms that.
TXI004 | wr_en held high continuously: TX sends frames back-to-back, re-latching data_in at each IDLE cycle. | Hold wr_en high for >= 5 frames; change data_in between frames. | scb_tx; mon_tx (one stop-bit period between frames) | cp_wr_en_held (>= 3 consecutive frames) | P2 | Not started | Spec decision: is continuous retrigger intended? Write the answer down either way.
TXI005 | busy rises the cycle after an accepted wr_en and falls when the stop bit begins. | Any frame. | a_busy_after_wr_en; mon_tx (busy fall coincides with stop-bit start) | c_busy_after_wr_en (vacuity) | P1 | Not started
RXF001 | RX receives a correct 8N1 frame: data_out == transmitted byte, rdy rises once per frame. | drv_rx sends directed and random bytes at nominal bit period (5208 clks) with idle gaps. | scb_rx: data_out compared when rdy rises | cg_rx_data.cp_data (same bins as cg_tx_data) | P1 | Not started | Needs drv_rx and the exposed rx pin.
RXF002 | RX samples at mid-bit: start bit checked 8 rx_ticks after detection, then one sample every 16 rx_ticks (data bits and stop bit). | Any frame. | a_rx_sample_spacing (ADD SVA, bound into receiver_block using state/sample/index) | cp_rx_index (0..7); cp_rx_sample_max (7 in START, 15 in DATA_OUT/STOP) | P1 | Not started | Internal-signal assertion. The sample point is up to one rx_tick (1/16 bit) late because detection is tick-granular.
RXF003 | Frame is received correctly for every alignment of the start edge relative to rx_tick. | drv_rx delays the start edge by 0..324 clks (sweep plus random). | scb_rx | cp_rx_edge_phase (>= 8 bins across 0..324) | P1 | Not started | The practical sampling-correctness test. rx passes through a 2-FF synchronizer, so this also shows the 2-clock input latency has no effect.
RXF004 | Back-to-back frames with zero idle gap: start bit immediately after the stop bit; all received. | drv_rx sends >= 100 frames with no gap, then with 1, 2 and 10-bit gaps. | scb_rx | cp_idle_gap (0, 1 bit, 2 bits, long) | P1 | Not started | RX leaves STOP at mid-stop-bit, which gives about half a bit of slack for the next start edge.
RXF005 | Constant-line patterns: 0x00 (9 low bits incl. start), 0xFF (data looks like idle), alternating 0x55/0xAA - all received correctly. | drv_rx sends each pattern singly and repeated back-to-back (e.g. 10x 0x00, 10x 0xFF). | scb_rx | cg_rx_data.cp_data bins 0x00, 0xFF, 0x55, 0xAA; cp_repeat (same byte >= 5x in a row) | P1 | Not started | 0x00 checks RX counts bit periods instead of waiting for edges; 0xFF after the start bit is indistinguishable from idle.
RXF006 | Idle line (rx=1) for a long time: rdy never rises and RX stays in IDLE. | Hold rx high >= 3 frame times after reset and between frames. | a_rdy_only_in_stop (ADD SVA: rdy rises only after RX state STOP) | c_rx_idle_long (rx high >= 3 frame times) | P2 | Not started
RXI001 | rdy stays high until rdy_clr, and data_out is held stable meanwhile. | Receive a byte; delay rdy_clr by 1 clk, half a frame, one frame. | a_rdy_holds; a_data_out_with_rdy | cp_rdy_hold_time (1 clk, < 1 frame, >= 1 frame) | P1 | Not started | A hold of >= 1 frame without a new byte needs an idle line afterwards.
RXI002 | rdy_clr clears rdy on the next cycle (a single-cycle pulse is enough). | 1-cycle rdy_clr pulse while rdy=1 and no frame completing. | a_rdy_clr_clears (ADD SVA: (rdy_clr && rdy && !completing) ¦=> !rdy) | c_rdy_clr_pulse - ADD | P1 | Not started | 'completing' = RX in STOP with sample==15 and rx_tick; take it from the receiver_block internals.
RXI003 | rdy_clr and a new byte completing in the same cycle: rdy ends up 1 (set wins over clear). | Directed: time rdy_clr to the cycle the RX STOP state completes (align using internal state/sample). | scb_rx: rdy stays 1 and data_out == new byte | c_rdy_clr_collision | P2 | Not started | Matches the RTL: rdy<=1 comes after rdy<=0 in the same always_ff. The existing cover only hits the case where rdy was already 1.
RXI004 | Overrun: a new frame completes while rdy is still 1. data_out is overwritten with the newest byte; no overrun flag. | Receive 2+ frames without rdy_clr. | scb_rx: data_out == newest byte (older byte lost) | c_overrun | P2 | Not started | Design limitation: no overrun flag. State it in the spec so it is not read as a miss.
RXE001 | Framing error (stop bit = 0): frame dropped - no rdy, data_out unchanged. | drv_rx sends frames with stop=0 and random data; then an idle-high gap of >= 1 frame and a good frame. | scb_rx (no rdy, data_out unchanged); a_rdy_only_in_stop | cp_stop_val (0, 1); FSM002 arc STOP->IDLE with rx_s=0 | P2 | Not started | No error flag. RX returns to IDLE at mid-stop with the line still low, so it re-detects a false start; record what happens on the following frame. Needs drv_rx.
RXE002 | Short glitch on an idle line (shorter than about half a bit) is rejected: START -> IDLE at sample 7, no rdy. | Pulse rx low for w clks, w in {1, 2, 10, 100, 325, 1000, 2000, 2500}; idle high otherwise. | scb_rx (no byte) | cp_glitch_width (< 1 rx_tick, 1-4, 5-7, >= 8 rx_ticks); FSM002 arc START->IDLE | P2 | Not started | Glitches narrower than one rx_tick may be missed entirely depending on alignment; either outcome passes. Needs drv_rx.
RXE003 | Characterise the glitch width at which a glitch is accepted as a start bit; expected result is a spurious 0xFF byte. | Sweep glitch width from about 0.4 to 1.6 bit in 1/16-bit steps. | scb_rx logs the threshold and the resulting byte (characterisation, not pass/fail) | cp_glitch_width (extended bins up to 1.6 bit) | P3 | Not started | A glitch still low at the mid-bit check looks like a real start; if it ends before the first data sample the byte is 0xFF with a valid stop. Record the threshold in the spec.
RXE004 | Break (rx held low >= 3 frame times): no rdy fires while the line is low. | Hold rx low for 1, 2, 3+ frame times, then return high and send a good frame. | scb_rx: no rdy during the break | cp_break_len (1, 2, 3+ frames) | P2 | Not started | RX keeps restarting during a break (each framing error leads to a new start). After release it can be mid pseudo-frame and emit one spurious byte - there is no break detection. Flush or tolerate one byte after release and document it.
RXE005 | Noise on a single sample: a flipped rx level at the mid-bit sample corrupts that bit (single-sample design, no majority vote). | Flip rx for >= 1 rx_tick centred on the sample point of data bit k, k = 0..7. | scb_rx expects bit k flipped (known limitation), or waive | cp_noise_bit (0..7) | P3 | Not started | Expected behaviour of this design. Either mark Waived with this reason, or add a 3-sample majority vote to the RTL and flip the expectation.
BDT001 | RX tolerates a transmitter bit-period offset of up to +/-2% from nominal. | drv_rx bit period = round(5208 x (1 + offset)) clks for offset in {-2%, -1%, 0, +1%, +2%}; >= 20 random bytes each, random start-edge phase. | scb_rx | cp_baud_offset (-2..+2 % bins) | P1 | Not started | Zero offset = 5208 clks (the TX period). RX's own period is 16 x 325 = 5200, so its true zero point is 0.15% lower.
BDT002 | Find the offset at which RX first fails; must pass through +/-3%. | Offsets -6% to +6% in 1% steps; >= 50 random bytes each. | scb_rx; log first failing offset in each direction | cp_baud_offset (-6..+6 % bins) | P2 | Not started | Hand estimate: failures start around +/-4 to 5% (the stop bit, sampled 9.5 bit times after the start edge, is the limit). Not simulated - record the measured limit in the spec.
PAR001 | Frame correctness over a parameter sweep of clk_freq and baud_rate. | Run the supported configs from Param_Calc: (50M, 9600), (50M, 115200), (50M, 312500), (100M, 115200), (25M, 9600); smoke test plus E2E001 on each. | mon_tx, scb_tx, scb_rx, SVA with CLKS_PER_BIT bound per config | cp_cfg (one bin per config) | P2 | Not started | Param_Calc shows the TX vs RX period mismatch per config. 312500 baud is 160 clks/bit - handy for long regressions.
PAR002 | Unsupported parameter combinations are identified and rejected, not left to fail silently. | Elaborate (50M, 921600) [TX/RX mismatch 11%], (50M, 3.125M) [RX max = 1, edge case], (50M, 6.25M) [RX max = 0]. | Review plus elaboration-time check (ADD: $error in an initial block when clk_freq < 16*baud_rate or mismatch > limit) | n/a (static check) | P3 | Not started | When RX max = 1, $clog2 gives 0 and the counter is declared [-1:0] (2 bits); the tick then fires every clock. Below that the divide gives 0 and RX is broken.
E2E001 | Loopback random traffic: every byte arrives once, in order, with the correct value. | >= 1000 random bytes, random idle gaps (0 to 3 frame times), rdy_clr latency 1 to 20 clks. | scb (in-order compare of TX queue vs RX data_out) | cg_e2e (cp_data x cp_idle_gap) | P1 | Not started | Keep rdy_clr latency well under one frame so overrun does not occur here (overrun is RXI004). 1000 frames at 9600 baud is about 52M clocks - use a faster baud config for long runs.
E2E002 | Directed data patterns end-to-end: 0x00, 0xFF, 0x55, 0xAA, 0x01, 0x80, walking 1 and walking 0, each repeated 10x. | Directed sequence through wr_en, loopback to data_out. | scb | cg_tx_data.cp_data and cg_rx_data.cp_data - all bins hit | P1 | Not started
E2E003 | Consecutive frames in loopback with zero gap: >= 100 frames with wr_en re-issued on every busy fall. | wr_en on the first cycle busy is low, random data. | scb; a_busy_after_wr_en | c_wr_en_at_busy_fall (hit count >= 100) | P1 | Not started | System-level version of TXI003 (this one also checks that RX keeps up).
E2E004 | Reset in the middle of loopback traffic: system recovers and the first frame after reset (plus idle) is received correctly. | Random rst during traffic; idle for one frame; send a frame; repeat. | scb (flushed on rst); a_rst_values | c_rst_mid_tx; cp_rx_state_at_rst | P2 | Not started | Expect the same junk-byte question as RST003 - idle the line before checking.
E2E005 | Full duplex: a TX frame and an independently driven RX frame in flight at the same time; both correct. | Start a TX frame and a drv_rx frame with random relative offset, different data. | scb_tx / mon_tx and scb_rx | cp_duplex_overlap (TX starts during RX START, DATA, STOP; and the reverse) | P2 | Not started | Needs the exposed rx pin. TX and RX share one baud generator, so they cannot drift against each other here.
FSM001 | TX FSM: all 4 states visited and all transitions taken (IDLE->START, START->DATA, DATA->DATA, DATA->STOP, STOP->IDLE) plus the hold loops waiting for tx_tick. | Union of all TX tests. | a_tx_fsm_legal (ADD SVA: no illegal state jumps) | cp_tx_state; cp_tx_trans (transition bins) in cov.sv | P1 | Not started | The default branch is unreachable (the 2-bit enum uses all 4 codes): exclude it from coverage and record the reason.
FSM002 | RX FSM: all 4 states and all transitions, including START->IDLE (false start) and STOP->IDLE with rx_s=0 (framing error). | Union of all RX tests, plus RXE001 and RXE002. | a_rx_fsm_legal (ADD SVA) | cp_rx_state; cp_rx_trans | P1 | Not started | The two error arcs are unreachable in loopback - they need drv_rx.
FSM003 | Counters reach full range and never exceed it: TX bit_count 0..7; RX index 0..7; RX sample 0..7 in START and 0..15 in DATA_OUT/STOP. | Union of all frame tests. | a_rx_sample_range (ADD SVA); a_tx_bitcount_range (ADD SVA) | cp_bit_count; cp_rx_index; cp_rx_sample | P2 | Not started
CDC001 | rx input is synchronised by a 2-FF chain before use (metastability protection). | Not testable in RTL simulation (no metastability model). | Manual review; CDC lint tool if available | n/a | P2 | Not started | The functional side effect (2-clock input latency) is exercised by RXF003. Record the review sign-off in Notes.

## Summary
UART verification plan - summary
Total plan rows | 44
Pass rate (excluding waived) | 0%
Rows with an SVA still to add | 9
Status by priority
Status | P1 | P2 | P3 | Total
Not started | 25 | 15 | 4 | 44
In progress | 0 | 0 | 0 | 0
Pass | 0 | 0 | 0 | 0
Fail | 0 | 0 | 0 | 0
Blocked | 0 | 0 | 0 | 0
Waived | 0 | 0 | 0 | 0
Total | 25 | 15 | 4 | 44
Rows with unrecognised status/priority | 0
By area
Area | ID prefix | Total | Pass | % Pass
Reset | RST | 5 | 0 | 0%
Baud generator | BRG | 2 | 0 | 0%
TX frame format and timing | TXF | 4 | 0 | 0%
TX host interface | TXI | 5 | 0 | 0%
RX reception and sampling | RXF | 6 | 0 | 0%
RX host interface | RXI | 4 | 0 | 0%
RX errors and robustness | RXE | 5 | 0 | 0%
Baud tolerance | BDT | 2 | 0 | 0%
Parameters | PAR | 2 | 0 | 0%
End-to-end | E2E | 5 | 0 | 0%
FSM and counter coverage | FSM | 3 | 0 | 0%
CDC | CDC | 1 | 0 | 0%
Total |  | 44 | 0 | 0%

## Components
Component | Role | Where | Status | Notes
Serial pin access (RTL change) | Expose tx as an output and rx as an input on UART and UART_if, with a loopback enable so rx is either tied to tx or driven independently. | UART.sv, UART_if.sv | Not started | Needed for every row that says 'Needs drv_rx', for full-duplex tests, and for decoding tx without hierarchical references. Keep loopback as the default so existing tests still work.
uart_sva.sv (assertions) | SVA checker module attached to UART with bind. Holds the a_* and c_* items named in the Checker and Coverage columns. | uart_sva.sv | Starter written, not simulated | 13 items written (a_rst_values, c_rst_after_traffic, c_rst_mid_tx, a_tx_tick_period, a_tx_idle_high, a_tx_changes_on_tick, a_busy_after_wr_en, c_wr_en_at_busy_fall, c_wr_en_while_busy, a_rdy_holds, a_data_out_with_rdy, c_rdy_clr_collision, c_overrun). Names marked ADD still need writing.
drv_wr (host driver) | Drives rst, wr_en, data_in and rdy_clr with directed and randomised timing (phase relative to tx_tick, back-to-back, held-high, rdy_clr delay). | testbench | Not started
mon_tx (independent TX monitor) | Watches the tx line, measures bit widths in clocks on a grid anchored on the start-bit edge, decodes the byte LSB first, flags aborted frames, checks busy fall against stop-bit start. | testbench | Not started | Must not share code or assumptions with the RTL; that independence is what makes it a real check.
drv_rx (serial RX driver) | Drives the rx line. Knobs: data, bit period in clocks, start-edge phase, stop-bit value, idle gap, glitch width and position, break length. | testbench | Not started | Depends on the serial pin access change.
scb_tx / scb_rx (scoreboards) | Queues of expected bytes compared against mon_tx output and RX data_out at the rdy rise. Flushed on reset. scb_rx must know about dropped, overrun and spurious-byte cases. | testbench | Not started
cov.sv (covergroups) | cg_* / cp_* items named in the Coverage column (data bins, FSM state and transition bins, phase bins, idle gap, glitch width, baud offset, config). | cov.sv | Not started | Name each covergroup exactly as in the plan so a row traces straight to its code.
Regression configs | Parameter sets for PAR001 plus a fast config (e.g. 50 MHz / 312500 baud) for long random runs. | run script | Not started | See Param_Calc for the supported and unsupported combinations.

## Param_Calc
Baud generator parameter check
Mirrors the integer divisions in baud_rate_generator.sv. Edit the blue cells to try other configs.
Mismatch risk threshold | 2% | Assumption: the hand estimate of RX baud tolerance is about +/-4 to 5%, so a TX/RX period mismatch above 2% leaves little margin. Not simulated.
clk_freq (Hz) | baud_rate | TX clks/bit | RX tick divisor | RX clks/bit (16x) | TX/RX mismatch | Verdict
50000000 | 9600 | 5208 | 325 | 5200 | 0.1536% | OK
50000000 | 115200 | 434 | 27 | 432 | 0.4608% | OK
50000000 | 312500 | 160 | 10 | 160 | 0% | OK
100000000 | 115200 | 868 | 54 | 864 | 0.4608% | OK
25000000 | 9600 | 2604 | 162 | 2592 | 0.4608% | OK
50000000 | 921600 | 54 | 3 | 48 | 11.11% | RISKY
50000000 | 3125000 | 16 | 1 | 16 | 0% | EDGE (RX divisor = 1)
50000000 | 6250000 | 8 | 0 | 0 | n/a | UNSUPPORTED
Default config is row 6 (50 MHz, 9600 baud): TX 5208 clks/bit, RX 325 x 16 = 5200.
RX divisor = 1 is the edge case: $clog2(1) = 0, so the RX counter is declared [-1:0] and the tick fires every clock. Divisor 0 breaks RX.

## Legend
How to use this workbook
Columns (Testplan sheet)
ID | Area prefix + number (RST, BRG, TXF, TXI, RXF, RXI, RXE, BDT, PAR, E2E, FSM, CDC). Summary counts by prefix.
Feature | One checkable statement of what must be true.
Stimulus | What the testbench does to exercise it.
Checker | The mechanism that FAILS if the feature is broken: an assertion, monitor or scoreboard check.
Coverage item | The cover property or covergroup bin that proves the scenario actually happened. A pass without this hit proves nothing.
Priority | P1 = core function, must pass before calling the design verified. P2 = error handling and corner cases. P3 = robustness extras and characterisation.
Status | Not started / In progress / Pass / Fail / Blocked / Waived. Give the reason for any Blocked or Waived in Notes.
What to edit
Yellow cells | Status (Testplan column G and Components column D) and the blue input cells on Param_Calc. Everything else can stay as is; add rows below the last one and the Summary picks them up (formulas read down to row 200).
Example row | Read RST001 as: after reset the outputs have their reset values (feature); hold rst, then re-apply it after a frame (stimulus); assertion a_rst_values fails if not (checker); c_rst_after_traffic proves the second case ran (coverage); P1; Not started.
Naming convention
a_* / c_* | SVA assert / cover directives. These live in uart_sva.sv. Where a row lists '(vacuity)', the cover is the assertion's antecedent, to catch an assertion that never triggered.
(ADD SVA) / ADD | Named in the plan but not yet written in uart_sva.sv. The Summary counts the Checker cells containing 'ADD SVA'.
mon_tx, drv_rx, drv_wr, scb_* | Testbench components, described on the Components sheet.
cg_* / cp_* | Covergroups and coverpoints in cov.sv.
Assumptions and sources
RTL read | baud_rate_generator.sv, transmitter_block.sv, receiver_block.sv, UART.sv and UART_if.sv from the UART folder of Ah-deee/sv_labs, as read during this conversation. uart_pkg.sv and cov.sv were empty.
Default numbers | clk_freq = 50,000,000 and baud_rate = 9600 are the defaults in baud_rate_generator.sv. They give 5208 TX clocks per bit and an rx_tick every 325 clocks (16 x 325 = 5200).
Baud tolerance | The +/-4 to 5% figure is a hand calculation (stop bit sampled 9.5 bit times after the start edge, start detection up to 1/16 bit late). It has not been simulated.
Glitch threshold | The 'about half a bit' figure comes from the 8-rx_tick start-bit check (8 x 325 = 2600 clocks of a 5200-clock bit). Not simulated.
Not simulated | Nothing in this plan has been run. Timing bounds in the assertions (for example the +1 slack in a_start_latency) may need adjusting after the first run.
Design limitations | No framing-error, overrun or break flags exist; those cases are dropped silently. The plan lists them so the spec can state it explicitly.